# Emergency Preparedness Planning guidelines April, 2023

Table of contents

List of acronyms	2

1	PIN & Emergency preparedness planning	2

2	How to develop your CP EPP	3

3	Who is in charge of emergency preparedness	3

3.1	Responsibilities	4

3.2	Follow-up mechanism	6

3.3	Archiving	6

4	How much does it take	7

5	Guidance for emergency preparedness planning	7

6	Lessons learned	10

# List of acronyms

CD – Country Director

CP – Country Program

EPP – Emergency Preparedness Plan

ERT – Emergency Response Team

EWS – Early Warning System

HoP/PD – Head of Programs / Programs Director

HoSO – Head of Systems & Operations

HU – Humanitarian Unit (HQ)

PM – Program Manager

# PIN & Emergency preparedness planning

Emergency preparedness means the ability to anticipate and respond timely and efficiently to both unexpected and recurrent disasters, and this requires having in place mechanisms and ensuring capacities to identify existing risks and to respond if/when the need arises. At PIN, emergency preparedness planning is formalized at each Country Program (CP) in the Emergency Preparedness Plan (EPP), composed of:

- Emergency preparedness Strategy: lays out what potential disaster risks exist in the country and, in case a disaster hits the country, the way PIN can address humanitarian needs quickly and efficiently. The strategy should focus on both sudden-onset (earthquakes, floods, tsunamis, etc) and slow-onset (drought, famine) disasters, including man-made disasters and conflicts. It should be a simple, short and practical guidance (max. 10 pages) for all CP staff.

- Emergency preparedness Action Plan: identifies the weaknesses and gaps in our emergency preparedness and comes up with the solutions on how we can improve our future performance at country level and in collaboration with HQ, by building our capacities and experience in emergency response.

To enhance its efficiency, make sure that your EPP is:

| Practical |  | Do not overcomplicate the EPP nor the planning process and always consider the topic from a real, operational point of view, trying to ensure practical guidance. |
| --- | --- | --- |
| Realistic |  | The EPP should not be a snapshot of “what we can do” but a realistic overview of our emergency response options in a given country. The risk mapping is not meant to be an exhaustive list of hazards but rather to consider hazards from the perspective of likelihood, severity/scope and geography/localization. The action plan should correspond to the CP capacities and predictable development – especially in terms of HR and humanitarian funding. It is recommended to also specify when PIN CP would not respond and the reasons why – for all teams, in particular future teams, to understand. |

# How to develop your CP EPP

Emergency preparedness planning is a 4-step process:

- EMERGENCY PREPAREDNESS BRAINSTORMING with senior management and the CP Emergency Response Team (ERT) if existing, to determine the approach and strategy of emergency preparedness in the CP – be sure to include experienced and knowledgeable national field staff. This step is the platform to develop the EPP including both the strategy and the action plan, as well as define the ERT if not in place.

- EMERGENCY PREPAREDNESS BRIEFING with the CP staff to introduce the emergency preparedness strategy, allocate tasks from the action plan and officially launch the EPP.

- OPTIONAL TECHNICAL SESSIONS for building the CP team’s capacities for emergency response, in sectors or themes that are relevant/in need e.g. how to conduct rapid assessments or distributions, how to mainstream protection or do no harm, or how to deliver cash-based responses, etc.

- ACTION PLAN IMPLEMENTATION: the development of the EPP is only the first step for emergency preparedness planning. Most important is the subsequent implementation of the action plan and the regular update of the EPP. Without follow-up and update, the EPP loses all significance and remains a useless piece of paper.

A template program is available in Annex A and guidance on the steps is detailed in section IV below.

# Who is in charge of emergency preparedness

The EPP should be driven by the country program, specifically by CP senior management. Remote or in-country support may be requested from the HQ Humanitarian Unit.

On the country program, emergency preparedness is the responsibility of everyone. In the event of a disaster, it is crucial to have a pre-established operational structure and line of responsibilities to ensure that PIN’s overall response runs smoothly from the initial stage and communication is not hindered.

## Responsibilities

| EPP responsibility level | Overall | Follow-up (follow-up on the action plan and annual EPP update) | Activation & leadership (Activation in case a crisis strikes) | Execution |
| --- | --- | --- | --- | --- |
| Responsible Person | Country Director | Anyone on the CP with oversight & coordination capacities e.g. CD, HoSO, HoP/PD, a relevant PM, etc. | Emergency Response Team Lead | Emergency Response Team |
| Notes | The Country Director holds the overall responsibility over the EPP. The CD is the final decision-maker at EPP design stage, and shares the responsibility with the ERT for deciding the activation of the EPP when a crisis occurs. | Overall implementation oversight may be with a single person but it is advised to involve more team members in the practical oversight, to ensure a realistic workload for each and encourage genuine progress. In this case, there should be a clear division of responsibility between each person in charge. For instance, the HoSO may be responsible to follow up on the EPP Action Plan while the HoP/PD may be responsible to ensure the annual update of the EPP strategy; or the follow up on the Action plan may be divided between different persons per section. | The ERT Lead is responsible, together with the CD, for deciding the EPP activation when a crisis strikes. The ERT Lead coordinates the ERT and leads the execution of the EPP. | In case of a major disaster, the ERT may be activated and redirected to support the emergency response as needed. Non-emergency activities may be temporarily suspended if the disaster is severe and prevents the implementation of regular activities. |

The Emergency Response Team (ERT) is a “dormant” team whose role may be activated when a disaster strikes: members of the ERT fulfil a regular function on the CP and may switch to their emergency role as needed. All CPs are expected to have their own ERT regardless of the current (non)existence of humanitarian programming on the CP.

Members of the ERT are identified by senior management but all members of the ERT should be volunteers and freely agree to be part of the ERT.

Each CP defines the structure of its ERT, however it is recommended to

- Include senior staff from logistics, finance & admin, security, programs and MEAL;

- Include both national and international staff;

- Nominate an ERT lead. The ERT lead should be the most experienced and relevant team member for coordinating a response e.g. it does not necessarily need to be the CD or HoP/PD but may be a strong PM with emergency experience or the HoSO or any other team member who is most competent for that role and can have decision power.

Responsibilities for the EPP and ERT membership should be included as a task in the relevant staff’s Job description and ToRs. Suggested points to integrate in the ToRs are included below:

- For the Overall role: Holds overall responsibility for the design, regular update and follow-up of the CP Emergency preparedness plan (EPP), ensuring progress on action plan and reporting to HQ during semi-annual country reviews

- For the Follow-up role: Leads the design, regular update and follow-up of the CP Emergency preparedness plan (EPP), ensuring regular progress on action plan and troubleshooting challenges and bottlenecks.

- For the Activation & Leadership role: Shares (with CD) responsibility to activate the Emergency Preparedness (EPP) Plan when a crisis strikes, and holds the overall leadership of the response based on the EPP.

- For the Execution role: Actively supports and contributes to the execution of the emergency preparedness plan (EPP) during an emergency, based on the tasks and responsibilities assigned as part of the EPP. [these tasks should be detailed per position e.g. a program officer will likely be engaged in the conduct of needs assessments while a logistician will support procurements or warehouse management, etc.]

Establish a communication tree and ensure the following responsibilities are clearly assigned (make sure workload allocation is realistic):

  - Human resources (recruitment, roster, capacity building)

  - Safety and security

  - Needs assessments (data collection and analysis, EWS, joint assessments)

  - Coordination & Partnerships (Alliance2015, Clusters, local/international partners, local authorities)

  - Fundraising and communication with donors (incl. Club of Friends and Alliance2015)

  - Logistics and Procurements, Finance

  - Communication/media/advocacy (collection of material, advocacy approach)

  - Communication with HQ

  - Document archiving

Example of an ERT organogram:

ERT Implementation team

(identified as needed, and detailed per position/team member)

(PMs, POs, field officers, MEAL officers/assistants, database manager, logisticians, financial managers/officers, Communication officers, CFRM officer, etc)

Coordination line

ERT implementation

ERT management team

## Follow-up mechanism

Regular follow-up

- The final emergency preparedness plan must be included in the Country strategy, with progress on it reported in semi-annual country review reports to HQ and in the CP checklist.

- At CP level, updates on the EPP, in particular on risks analysis/forecast and Action plan progress, should be part of regular meetings (ideally monthly or bi-monthly) that already occur at CP level. For instance updates may be integrated within the regular SMT meetings or any other format as relevant, as long as all departments participate/are represented.

Annual update

- EPPs should be regularly updated to ensure that they remain relevant, and to identify new action points. Annual updates are sufficient in general but in very volatile contexts more frequent updates may be required to ensure that risks are adequately identified and understood and the designed response system remains relevant to evolving threats and contexts.

## Archiving

EPPs are archived in ELO, in the following folder:

- 16 – Operational documents

- RDD

- ARM000

- 02a_Emergency Preparedness Planning

# How much does it take

The initial exercise for emergency preparedness planning is a low-cost exercise but one that requires continuous engagement. Below are listed key requirements (standardized estimation):

- Estimated standard timeline and participants:

- Estimated standard costs:

  - Facilitator flight and accommodation – 1 x return flight, up to 8 nights (more if optional sessions), est. up to 1,500 EUR (NB: the facilitator may also be supporting remotely part or all of the time)

  - Facilitator’s salary for 3 to 8 working days – est. 300 EUR to 1,000 EUR

  - EPP Briefing – stationary, refreshments and venue rental for half a day, est. 200 EUR

Total cost: between 200 EUR (no HQ facilitator involved) and 2,700 EUR

! Additional costs may be incurred in case optional trainings are planned e.g. venue rental, trainer’s fee, potentially staff accommodation if staff is drawn in from the field or other offices, etc.

# Guidance for emergency preparedness planning

| STEP 1 EMERGENCY PREPAREDNESS BRAINSTORMING (EPP development) |  |
| --- | --- |
| Purpose | To discuss and determine the EPP aims, strategy and process, defining the core elements of the emergency preparedness strategy and its action plan. |
| Audience | Country Program Senior Management + ERT (if in place) |
| Duration | 0.5 day |
| Step 1.1 | Introduction to emergency preparedness planning and PIN Strategy for humanitarian response & recovery |
| Duration Purpose Guidance Material | 15-30 min To introduce the topic of EPP and ensure all participants all have the minimum knowledge and understanding of PIN’s strategy for emergency response & recovery. Prior to the workshop, ask participants to go through PIN’s strategy for emergency response & recovery. Use the available PowerPoint presentation if your participants are not well versed in the humanitarian sector and not familiar with the strategy. If participants know the strategy and/or are experienced in the humanitarian sector, you may keep this step short and use a more participative approach (asking for example how is the strategy implemented in the CP, what are the key issues relevant for the CP, what is working well or not well, etc., rather than going through the PPT). 1. PIN Emergency response.pptx |
| Step 1.2 | Country risk identification |
| Duration | 30min - 1 hour |
| Purpose | To introduce the country specific hazards, its disaster history and DRM structure, discuss the current knowledge and experience of team (esp. national colleagues) and categorize risks according to severity/frequency |
| Guidance | If a risk matrix/analysis exists for the country/region (e.g. by OCHA, state agency or other actor) use it and discuss it with the team - you can keep this exercise very short. If no risk matrix exists, conduct a desk research in advance, let participants comment on what you have found out and engage them to prioritize risks by analyzing the frequency and severity of potential disasters. Be aware that people may have been directly affected by disasters discussed and address questions sensitively. |
| Material | 2. Risk matrix – Handout (if external risk matrix exists, use it instead of the handout) |
| Step 1.3 | Response options |
| Duration | 1 hour |
| Purpose | To establish impact and response scenarios based on the main risks identified before |
| Guidance | Prior to the workshop, prepare 1-2 country-specific, realistic case studies with questions, and if possible, share them with participants for them to think about prior to the session. During the session, discuss each case study, discussing and defining in particular: - Geographic areas: determining in which regions PIN could realistically assess and/or respond and in which it could not due to logistical or other challenges), - Thresholds: at which point would PIN assess and/or respond, what criteria need to be met for PIN to assess/respond, in terms of people affected but also of funding availability (immediate and short/medium term), declaration of state of emergency and call for international help by the national authorities, access to the areas, etc - Sectors of response (possibly activities) and justification for the exclusion of others - Partnerships (especially with local partners) and support to existing emergency response mechanisms (government, local Red Cross, etc) If you have a larger group e.g. 8-10 people, you may split them in groups and ask each group to discuss one case study. |
| Material | 3a. Sample case studies 3b. Answer sheet with standard questions |
| Step 1.4 | Gap analysis |
| Duration | 2 hours |
| Purpose | To identify the gaps in the current country program structure and resources and discuss the steps to take to address them in the next 12 months. |
| Guidance | This session should be informed by the results of the previous session, covering topics such as human resources, Logistics and financial processes and systems, funding and fundraising, coordination and partnerships (including A2015), security, thresholds of intervention. Use the Exercise 4 Answer Sheet and a projector to enter ideas in real time. |
| Material | 4. Emergency preparedness Action plan – Template 5. Checklist for Emergency Preparedness planning |

| STEP 2 EMERGENCY PREPAREDNESS BRIEFING |  |
| --- | --- |
| Purpose | To introduce the emergency preparedness plan and launch the implementation of the action plan |
| Audience | Country Program team |
| Duration | 0.5 day |
| Guidance | Organize a session with the whole CP team to introduce the emergency preparedness strategy, go through the action plan in detail and allocate roles and responsibilities. This should serve as the official launch of the EPP, with the action plan being set in motion. Allow a Q&A session to answer all potential questions or requests for clarification. |
| Material | 4. Emergency preparedness Action plan 6. Emergency preparedness Strategy |

| STEP 3 CAPACITY & SKILLS BUILDING SESSIONS (OPTIONAL) |  |
| --- | --- |
| Purpose | To ensure the emergency preparedness plan and official launch the implementation of the action plan |
| Audience | Country Program team |
| Duration | 2h and more |
| Step 3.1 | Disaster simulation |
| Duration | 0,5 day |
| Purpose | To promote practical understanding of emergency preparedness within the country program team and ensure takeover of the action plan. |
| Guidance | Organize, following the briefing, a disaster simulation exercise with the CP team, to provide them the space to recognize and understand for themselves certain gaps and weaknesses in the CP structure – such as the lack of pre-identified suppliers or undefined communication trees. This will facilitate the team’s takeover and ownership of the action plan, while also providing a useful platform to identify staff for the roster and potential previously unidentified capacity building needs. |
| Material | 4. Emergency preparedness Action plan 6. Emergency preparedness Strategy |
| Step 3.1 | Technical skills |
| Duration | As needed |
| Purpose | To ensure sufficient minimum knowledge and skills for emergency response within the ERT and among the country program staff as required |
| Guidance | It is recommended to include one or more session on the practical emergency response skills that might be new to teams – for example on rapid needs assessments, organising distributions; according to identified knowledge gaps. The topics of the technical sessions should be tailored to the individual needs of a given CP and should be determined by the CP, with support from a HU advisor if necessary. The sessions may be taken on-line delivered inhouse by an experienced CP staff, by an HQ HU advisor or be provided externally if such opportunities exist in the CP – for instance CaLP often organizes trainings on cash-based responses, a WASH cluster partner on WASH, etc. Search for them and utilize them as relevant. |
| Material | PIN humanitarian e-learnings PIN Humanitarian induction modules, tailored sessions |

STEP 4 EMERGENCY PREPAREDNESS PLAN IMPLEMENTATION

Start implementing the action plan. Include it in the Country strategy, revise it annually (or bi-annually depending on the profile of the country), and report on the implementation progress in semi-annual country reviews.

# Lessons learned

- Refer to existing resources: keep the EPP simple, don’t overload it with information. Rather than copy-pasting or paraphrasing existing material, put key information in bullet points/tables and refer to relevant internal or external resources. OCHA often produces risk analyses as part of its country needs overview, and in certain countries state agencies, such as disaster management agencies, also produce or have risks analysis available, so be sure to check them and refer to them rather than trying to reinvent the wheel.

- Flexibility is key. Avoid detailing scenarios and response plans too much.  The aim of the EPP is not to detail exactly how PIN will respond in a crisis and how many beneficiaries it will cover, but rather to lay out principles and approaches of response. Scenarios are only meant to facilitate the discussion and identify key areas, sectors and activities that PIN may engage in, models of response, and redlines. The reality is always widely different than what we can ever plan. Make sure to remain flexible – and make sure this flexibility is retained across the team.

- Be realistic and practical. Avoid listing too many action points in the EPP Action plan, but rather focus on 2-3 fundamental ones that may have a real impact on our ability to respond effectively. Address them in the next 12 months, and once they are completed, identify new action points at the next EPP update.

- Keep key team members in the loop: EPP is one of the many priorities on a CP, and it can easily be overlooked especially when there is a turnover. To avoid the EPP from getting “lost”, have more responsible persons involved at various levels, include EPP in their ToRs, and make sure to integrate regular EPP updates within existing coordination mechanisms such as SMT meetings or other regular coordination meetings (involving all departments).